## 1. Design Targets
Vehicle Design and Peformance Targets
Sr. No. | Items | Details
1 | Team ID | 21028
2 | Team Name | INVINCIBLES 5.0
3 | Kerb Weight (kg): | 112
4 | Length (mm): | 2189.48
5 | Length (inch): | 86.2
6 | Width (mm): | 594.614
7 | Width (Inch): | 58
8 | Height (mm): | 1701.8
9 | Height (inch): | 67
10 | Max speed (km/h): | 57.006
11 | Maximum acceleration (m/s²): | 1.533
12 | Gradeability (degree): | 6.43
13 | Turning radius (m): | 2.7325
14 | Turning radius (inch): | 107.578
15 | Battery Runtime (Minutes): | 168

## 2. Project Plan
Efficycle Project Plan |  |  |  | Team ID |  | 21028 | [5 empty] | Legends |  | MAIN TASK/ACTIVITY |  |  |  | MILESTONES
SUB TASK/ACTIVITY
|  |  |  | Team Name |  | INVINCIBLES 5.0
[14 empty] | MILESTONE TEXTS |  |  |  | ADDITIONAL INFO
Task ID | Task/Activity Description | Duration (Days) | Start Date | End Date | Responsible | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
[6 empty] | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22
[6 empty] | 1/06 | 07/06 | 14/06 | 21/06 | 28/06 | 01/07 | 12/07 | 19/07 | 26/07 | 02/08 | 09/08 | 16/08 | 23/08 | 30/08 | 06/09 | 13/09 | 20/09 | 27/09 | 04/10 | 11/10 | 18/10 | 25/10 | 01/11 | 08/11 | 15/11 | 22/11 | 29/11 | 06/12 | 13/12 | 20/12 | 27/12 | 03/01 | 10/01 | 17/01 | 24/01 | 31/01 | 07/02 | 14/02 | 21/02 | 28/01 | 07/03 | 14/03 | 21/03 | 28/03 | 04/04 | 11/04 | 18/04 | 25/04 | 02/05 | 09/05 | 16/05 | 23/05 | 30/05
A | Research | 25 | 2021-06-06 | 2021-06-30 | Ankitha
A.1 | Basic Idea on Efficycle | 5 | 2021-06-06 | 2021-06-10 | Ankitha
A.2 | Understanding Rulebook | 5 | 2021-06-11 | 2021-06-15 | Pratik
A.3 | Subsystem Exploration | 15 | 2021-06-16 | 2021-06-30 | Gaurav
B | Design and CAD Modelling | 61 | 2021-07-01 | 2021-08-30 | Sufyaan
B.1 | Hand Sketch Preparation | 7 | 2021-07-01 | 2021-07-07 | Surya
B.2 | Chassis Sketch (Mock) | 8 | 2021-07-08 | 2021-07-15 | Yasin
B.3 | Chassis Design | 25 | 2021-07-16 | 2021-08-09 | Sufyaan
B.4 | Electrical Design (With Circuits) | 5 | 2021-08-01 | 2021-08-05 | Gaurav
B.5 | Subsystem Designing | 33 | 2021-07-25 | 2021-08-30 | Bharath
B.6 | Suspension Design | 14 | 2021-07-25 | 2021-08-08 | Abhinava
B.7 | Transmission Design | 15 | 2021-07-25 | 2021-08-09 | Sailaja
B.8 | Breaking Design | 7 | 2021-07-25 | 2021-08-01 | Pratik
B.9 | Steering Design | 18 | 2021-08-13 | 2021-08-30 | Pujitha
C | CAE Analysis | 40 | 2021-08-11 | 2020-09-19 | Yasin
C.1 | Front Impact,Side Impact Analysis | 7 | 2021-08-11 | 2021-08-17 | Yasin
C.2 | Front and Side roll Analysis | 7 | 2021-08-18 | 2021-08-24 | Sufyaan
C.3 | Static Structural Analysis | 10 | 2021-08-25 | 2021-09-03 | Sharan
C.4 | Hardpoint, Bending, Tortional Analysis | 2 | 2021-09-04 | 2021-09-05 | Yasin
C.5 | RULA Analysis | 2 | 2021-09-06 | 2021-09-07 | Sharan
C.6 | Optimisation | 32 | 2021-08-19 | 2021-09-19 | Sufyaan
D | Sponsorship and Procurement | 52 | 2021-09-20 | 2021-11-10 | Gaurav
D.1 | Sponsorship | 30 | 2021-09-20 | 2021-10-19 | Sailaja
D.2 | Frame Material | 14 | 2021-09-30 | 2021-10-13 | Sufyaan
D.3 | Electrical Circuit System | 20 | 2021-10-01 | 2021-10-20 | Ankitha
D.4 | Wheels & Brakes | 7 | 2021-10-10 | 2021-10-17 | Pratik
D.5 | Steering | 12 | 2021-10-14 | 2021-10-25 | Pujitha
D.6 | Gear and Drive Train | 13 | 2021-10-21 | 2021-11-02 | Bharath
D.7 | Suspension | 10 | 2021-10-26 | 2021-11-04 | Abhinava
D.8 | Miscellaneous | 6 | 2021-11-05 | 2021-11-10 | Arshiya
E | Virtual Event Complete | 183 | 2021-06-06 | 2021-12-05 | Abhinava
E.1 | Package-1 Submission | 2 | 2021-09-20 | 2021-09-21 | Abhinava
E.2 | Package-2 Target Submission | 3 | 2021-10-15 | 2021-10-17 | Abhinava
F | Fabrication | 61 | 2021-10-11 | 2021-12-20 | Sailaja
F.1 | PVC Prototype | 9 | 2021-10-11 | 2021-10-20 | Vani
F.2 | Material Testing & Analysis | 7 | 2021-10-20 | 2021-10-27 | Sailaja
F.3 | Frame Building | 25 | 2021-10-28 | 2021-11-24 | Pujitha
F.4 | Assembly of Drive Components | 21 | 2021-11-14 | 2021-12-05 | Vani
F.5 | Intergrating All Components | 14 | 2021-11-30 | 2021-12-14 | Abhinava
F.6 | Ergonomics | 5 | 2021-12-15 | 2021-12-20 | Yasin
G | Evaluation and Completion | 30 | 2021-12-21 | 2022-01-19 | Vani
G.1 | Vechile Completion | 6 | 2021-12-21 | 2021-12-26 | Gaurav
G.2 | Mock Dynamic Tests | 9 | 2021-12-27 | 2022-01-04 | Ankitha
G.3 | Working Inspection | 6 | 2021-01-05 | 2022-01-10 | Surya
G.4 | Static Evaluation | 9 | 2021-01-11 | 2022-01-19 | Pujitha
Text
SUBSYTEM DESIGN COMPLETE
DESIGN COMPLETE
VIRTUAL EVENT COMPLETE
EFFICYCLE COMPLETE
SPONSORSHIP COMPLETE
ANALYSIS COMPLETION
Assembly of Steeing, Brakes, Suspension, etc
Clearance Inspection with respect to the rider and the ground.
PACKAGE-1 SUBMITTED
FABRICATION COMPLETION
Market survey (including avability) with quotation Invoice collections.
ELECTRICAL COMPONENTS MOUNTING COMPLETION
PAINTS, LOGOS, SHEET METAL, SEATS MOUNTING, ETC